## Sprint_Backlog_progress
GROUP F CMM004 PROJECT REPORT

PROJECT NAME: FTEAM FASHION WEB DESIGN

PRODUCT BACKLOG:
1	WEBAPP Brand name and home page design(index.html)
2	owner should be able to upload items for sales
3	buyer should be able to create account
4	buyer should be able to sign into account with an email and password
5	Buyer/Visitor should be able to view and access items
6	Buyer should be able to pay for selected items in the website cart
7	Buyer should be able to search for items by category and price
8	Buyer should be able to purchase and request for online delivery

Product Backlog Order priority
1	The Homepage of the Product (index.html)
2	Product database development
3	Owner should be able to upload items for sale
4	Buyer should be able to create an account, sign-in with e-mail and password

5	Buyer/Visitor should be able to view and access items
6	Buyer should be able to search for items by category and price
7	Buyer should be able to pay for selected items in the website cart
8	Buyer should be able to purchase and apply for online delivery

SPRINT BACKLOG:

Description	Effort level	evaluation criteria	evaluation remarks
Sprint 1: Creating home page using html, css, and java script	6 days	Home page should be successfully launched in the web browser.	functional	PRIORITY ALERT!!
				1. Creating database using php and MySQL

Sprint 2 : Creating database using php and MySQL	5 days	Successful deployment of database	pending	2. Database must be created and login enabled.

Sprint 3 : Development of the product page	5 days	Seller should be able to upload products, specify the price, and categorize the items	functional

Sprint 4: Buyer should be able to create an account, sign-in with e-mail and password	4 days	User is able to register/login	pending

## Weekly_peronal_progress_report
GROUP F CMM004 PROJECT REPORT

PROJECT NAME: FTEAM FASHION WEB DESIGN

PRODUCT BACKLOG:
1	WEBAPP Brand name and home page design(index.html)
2	owner should be able to upload items for sales
3	buyer should be able to create account
4	buyer should be able to sign into account with an email and password
5	Buyer/Visitor should be able to view and access items
6	Buyer should be able to pay for selected items in the website cart
7	Buyer should be able to search for items by category and price
8	Buyer should be able to purchase and request for online delivery

Weekly progress report for Team F

Week of ___________________	12-02-2023

Team Name		Plans	Progress	Challenges	Suggestions/comments	Date Achieved
Abidemi Sanusi		Create Report template for the project	report template created	No prior report template to adapt/adopt	report template is work in progress and can be improved upon by other members of the team	17-02-2023

		Create initial html index and push to repository	Done	Accessing group repository from private repository	The team need to learn more on github usage	17-02-2023

## Sitemap
GROUP F CMM004 PROJECT

					FTeam Fashion Sitemap

Homepage			About us		Fashion - Male			Fashion - Female			Check-out and Delivery option