## Sprint_Backlog_progress
GROUP F CMM004 PROJECT REPORT

PROJECT NAME: FTEAM FASHION WEB DESIGN

PRODUCT BACKLOG:
1	WEBAPP Brand name and home page design(index.html)
2	owner should be able to upload items for sales
3	buyer should be able to create account
4	buyer should be able to sign into account with an email and password
5	Buyer/Visitor should be able to view and access items
6	Buyer should be able to pay for selected items in the website cart
7	Buyer should be able to search for items by category and price
8	Buyer should be able to purchase and request for online delivery

Product Backlog Order priority
1	The Homepage of the Product (index.html)
2	Product database development
3	Owner should be able to upload items for sale
4	Buyer should be able to create an account, sign-in with e-mail and password

5	Buyer/Visitor should be able to view and access items
6	Buyer should be able to search for items by category and price
7	Buyer should be able to pay for selected items in the website cart
8	Buyer should be able to purchase and apply for online delivery

SPRINT BACKLOG:

Description	Effort level	evaluation criteria	evaluation remarks
Sprint 1: Creating home page using html, css, and java script	6 days	Home page should be successfully launched in the web browser.	functional	PRIORITY ALERT!!
				1. Creating database using php and MySQL

Sprint 2 : Creating database using php and MySQL	5 days	Successful deployment of database	pending	2. Database must be created and login enabled.

Sprint 3 : Development of the product page	6days	Seller should be able to upload products, specify the price, and categorize the items	functional

Sprint 4: Buyer should be able to create an account, sign-in with e-mail and password	4 days	User is able to register/login	pending

## Weekly_peronal_progress_report
GROUP F CMM004 PROJECT REPORT

PROJECT NAME: FTEAM FASHION WEB DESIGN

PRODUCT BACKLOG:
1	WEBAPP Brand name and home page design(index.html)
2	owner should be able to upload items for sales
3	buyer should be able to create account
4	buyer should be able to sign into account with an email and password
5	Buyer/Visitor should be able to view and access items
6	Buyer should be able to pay for selected items in the website cart
7	Buyer should be able to search for items by category and price
8	Buyer should be able to purchase and request for online delivery

Personal Weekly progress report for Team F Members

Team Name		Plans	Progress	Challenges	Suggestions/comments	Date Achieved
Abidemi Sanusi		Create Report template for the project	report template created	No prior report template to adapt/adopt	report template is work in progress and can be improved upon by other members of the team	17-02-2023

		Create initial html index and push to repository	Done	Accessing group repository from private repository	The team need to learn more on github usage	17-02-2023

Abidemi	Sanusi	reviewed HTMl files and make appropriate changes	Done	None	None	25/02/2023

Abidemi	Sanusi	file management and ensuring all group membes are able to work with the repository without disarranging the files	Continuous	Few team members require more information to keep the repository tidy	I suggest all members should make more effort in this regard to keep all files tidy	01/03/2023