## Sprint_Backlog_progress
GROUP F CMM004 PROJECT REPORT

PROJECT NAME: FTEAM FASHION WEB DESIGN

PRODUCT BACKLOG:
1	WEBAPP Brand name and home page design(index.html)
2	owner should be able to upload items for sales
3	buyer should be able to create account
4	buyer should be able to sign into account with an email and password
5	Buyer/Visitor should be able to view and access items
6	Buyer should be able to pay for selected items in the website cart
7	Buyer should be able to search for items by category and price
8	Buyer should be able to purchase and request for online delivery

Product Backlog Order priority
1	The Homepage of the Product
2	Buyer should be able to create an account
3	Owner should be able to upload items for sale
4	Buyer should be able to sign in with an email and password
5	Buyer/Visitor should be able to view and access items
6	Buyer should be able to search for items by category and price
7	Buyer should be able to pay for selected items in the website cart
8	Buyer should be able to purchase and apply for online delivery

SPRINT BACKLOG:

Description	Effort level	evaluation criteria
Sprint 1: To be able to create an account we need to have i) a database design. Ii) Interface Design.	7 days	Items		PRIORITY ALERT!!
				1. FUNCTIONAL WEBAPP MUST BE READY NEXT WEEK

Sprint 2: Linking interface and database	3 days	1. User (buyer) is able to login/ see their user profile 2. User (seller) should be able to upload products		2. DATABASE MUT BE CREATED AND LOG IN ENABLED

Sprint 3: User interface (JavaScript, display of website and navigation)	5 days	b. Functionality test

Sprint 4: Using search filter to search for items by price and category. (JavaScript) price range, size, colour, etc.	3 days	Code accuracy

Sprint 5: Once payment is initiated, order placed shows.	5 days	Payment Acceptability

Sprint 6: Delivery service or pick up after order is placed.	3 days	Delivery page

## Weekly_peronal_progress_report
GROUP F CMM004 PROJECT REPORT

PROJECT NAME: FTEAM FASHION WEB DESIGN

PRODUCT BACKLOG:
1	WEBAPP Brand name and home page design(index.html)
2	owner should be able to upload items for sales
3	buyer should be able to create account
4	buyer should be able to sign into account with an email and password
5	Buyer/Visitor should be able to view and access items
6	Buyer should be able to pay for selected items in the website cart
7	Buyer should be able to search for items by category and price
8	Buyer should be able to purchase and request for online delivery

Weekly progress report for Team F

Week of ___________________	12-02-2023

Team Name		Plans	Progress	Challenges	Suggestions/comments	Date Achieved
Abidemi Sanusi		Create Report template for the project	report template created	No prior report template to adapt/adopt	report template is work in progress and can be improved upon by other members of the team	17-02-2023

		Create initial html index and push to repository	Done	Accessing group repository from private repository	The team need to learn more on github usage	17-02-2023

## Sitemap
GROUP F CMM004 PROJECT

					FTeam Fashion Sitemap

Homepage			About us		Fashion - Male			Fashion - Female			Check-out and Delivery option